## Slide 1: Test Organisation

## Slide 2: Who does the testing?
Programmers do the ad hoc testing (and perhaps structured unit level testing)
Programmers, or other team members may do sub-system testing
Independent teams usually do system testing
Users (with support) perform the user acceptance testing
Independent organisations may be called upon to do any of the above testing formally.

## Slide 3: Test team roles
Test manager (test lead)
  plan, organise, manage and control the testing
  a project manager for the testing activities
Tester
  prepare test procedures, data, environments, expected results
  execute tests and log incidents
  execute re-tests and regression tests

## Slide 4: Test team roles
Test analyst
  to scope the testing, conduct expert interviews
  document test specifications
  liaison with test environment manager, technicians, users, testers
  prepare test reports.
Test automation technician
  record, code and test automated scripts
  prepare test data, test cases and expected results
  execute automated scripts, log results and prepare reports.

## Slide 5: Support staff
DBA to help find, extract, manipulate test data
System, network administrators
Toolsmiths to build utilities to extract data, execute tests, compare results etc.
Experts to provide direction
  technical
  business.

## Slide 6: Test Planning and Estimation

## Slide 7: Test plans are often layered

## Slide 8: Test planning
Planning is influenced by the test policy of the organization, the scope of testing, objectives, risks, constraints, criticality, testability and the availability of resources
Planning and re-planning takes place throughout the project
Test planning is necessarily a non-deterministic exercise where judgement and experience should be complemented with appropriate metrics as a means to managing the uncertainty.

## Slide 9: Test planning activities
Defining the overall approach to testing
Integrating testing activities into the overall plan
Scoping, assigning responsibilities, setting entry/exit criteria
Assigning resources for the different tasks defined
Defining the amount, level of detail, structure and templates for the test documentation
Selecting metrics for monitoring and controlling test preparation and execution, defect resolution and risk issues
Setting the level of detail for test procedures in order to provide enough information to support reproducible test preparation and execution.

## Slide 10: Exit criteria
The purpose of exit criteria is to define when to stop testing, such as at the end of a test level or when a set of tests has a specific goal.
Typically exit criteria may consist of:
  Thoroughness measures, such as coverage of code, functionality or risk
  Estimates of defect density or reliability measures
  Cost
  Residual risks, such as defects not fixed or lack of test coverage in certain areas
  Schedules such as those based on time to market

## Slide 11: Exit Criteria 2
Exit criteria should be objective and measurable
  all tests run successfully
  all faults found are fixed and re-tested
  coverage target (set and) met
  time (or cost) limit exceeded
Coverage items defined in terms of
  requirements, conditions, business transactions
  code statements, branches.

## Slide 12: Component Integration test completion criteria
Structural coverage
  100% coverage of transfers of control or data between components in scope
Functional coverage
  100% equivalence partitions for all message and function call parameters (valid and invalid values)
  100% valid transfers of control and data
  100% invalid/erroneous transfers of control or data
All tests passed without failure
All faults raised, corrected, retested, signed off.

## Slide 13: Typical (Functional) System Test completion criteria
Functional coverage
  100% equivalence partitions
  100% boundary values
  100% transaction flows identified in Functional Specification
All tests passed without failure
All incidents raised, corrected, retested, signed off OR waived by Product Assurance Team.

## Slide 14: Acceptance Test completion criteria
Acceptance criteria are business oriented
  100% of all critical system features (Business Requirements Spec and Reqs/Function matrix)
  100% branch testing through high priority business processes
  100% process coverage of medium priority business processes
  100% coverage of low priority business processes (at least once)
All tests (deemed high priority) passed without failure
All incidents raised, corrected, retested, signed off OR waived by Testing Board.

## Slide 15: End of Session 1
Any Questions?

## Slide 16: Large Scale Integration Test completion criteria
Similar to acceptance tests
Structural coverage
  100% coverage of data transfers between systems in scope
Functional coverage
  100% critical process flows (ref. Business System Architecture spec)
Example : 100% success rate for bank transfer regression test (250,000 records)
All incidents raised, corrected, retested, signed off.

## Slide 17: Defect Severity & Priority

## Slide 18: Defect Severity
Severity: the extent to which the defect can affect the software. Can be of following types (sometimes companies use numbers, i.e. 1-5 severity types):
(1) Critical: The defect that results in the termination of the complete system or one or more components of the system and causes extensive corruption of the data. There is no acceptable alternative method to achieve the required results.
(2) Major: The defect that results in the termination of the complete system or one or more components of the system and causes extensive corruption of the data. The failed function is unusable but there exists an acceptable alternative method to achieve the required results.
(3) Moderate: The defect that does not result in the termination, but causes the system to produce incorrect, incomplete or inconsistent.
(4) Minor: The defect that does not result in the termination and does not damage the usability of the system and the desired results can be easily obtained by working around the defects.
(5) Cosmetic: The defect that is related to the enhancement of the system where the changes are related to the look and feel of the application.

## Slide 19: Defect Priority
Priority: defines the order in which we should resolve a defect. Can be of following types (sometimes companies use numbers, i.e. 1-3 priority types):
(1) Low: The defect is an irritant which should be repaired, but repair can be deferred until after more serious defect have been fixed.
(2) Medium: The defect should be resolved in the normal course of development activities. It can wait until a new build or version is created.
(3) High: The defect must be resolved as soon as possible because the defect is affecting the application or the product severely. The system cannot be used until the repair has been done.
Sometimes, the priority can be escalated upward based on the reporter.

## Slide 20: Defect Severity and Priority
High Priority & High Severity: An error which occurs on the basic functionality of the application and will not allow the user to use the system.
High Priority & Low Severity: The spelling mistakes that happens on the cover page or heading or title of an application.
High Severity & Low Priority: An error which occurs on the functionality of the application (for which there is no workaround) and will not allow the user to use the system but on click of link which is rarely used by the end user.
Low Priority and Low Severity: Any cosmetic or spelling issues which is within a paragraph or in the report (Not on cover page, heading, title).

## Slide 21: Decision time
When deadline arrives, may have to stop tests now
  Some faults may be acceptable (for this release)
  Some tests may not be run at all
Might have to relax the exit criteria – assess the risk and agree with customer and document the changes
  (release the software now, but testing could continue)
If exit criteria are met, the software/system can be released to the next test phase or production
What if you finish the test plan very early?
  Have you done enough?
  Strengthen the exit criteria, perhaps and create more tests?

## Slide 22: Test Estimation

## Slide 23: Why do we need to estimate?
The Project Manager wants you to predict:
  how long testing will take in elapsed time
  how much effort will be needed
  when specialist skills/resources may be required
Resources can be testers, external consultants or services, tools, environments, hardware or software.

## Slide 24: What is an estimate?
For each task or activity...
  e.g. prepare a test plan, or procedure
What resources are required:
  people, tools, test environments etc.
  for how long?
  what is the resource utilisation? Full time, 50%, occasionally?
  what is the lead time for obtaining that resource?

## Slide 25: Test Estimation
Estimation is not an exact science
It's an approximate calculation or judgement based on:
  direct experience
  related experience
  informed guesswork.

## Slide 26: Usually a 'bottom-up' activity
Break down large complex tasks into smaller, simpler tasks to start with
Estimation 'in the small' is easier to do but.…
  do you estimate in days, hours (minutes?)
  it takes more effort to estimate large numbers of tasks
  contingencies add up (you may overdo it)
  some tasks may overlap (double accounting); some tasks may be incomplete (inadequate estimate).

## Slide 27: What do we need estimates of?
Just about everything
Need estimates for all explicit activities:
  test planning, design, implementation, execution
  early meetings, test environment, standards/document templates
Also need to consider 'follow-up' activities:
  re-testing, incident reviews, shut-down and clean-up, handover.

## Slide 28: What gets forgotten?
Training
'True' cost of tools (selection, pilot, implementation and roll-out)
Relocation of people, desks, comms, pcs etc
Reading time, 'getting up to speed'
Meetings and interviews take elapsed time to organise
'QA' and reviews as zero-duration tasks
Contingency.

## Slide 29: Contingency
Contingency is not a cop-out
You never have complete information, so estimation is imprecise and prone to error
Contingency accounts for potential under-estimation
Some tasks may not require contingency
Agree a percentage contingency on the risky tasks e.g. 10% or 15%

## Slide 30: Problems in estimating
Total effort for testing is indeterminate
  you can't predict how many faults will occur
  you can't predict their severity
  you can't predict time taken to fix
  you can't predict when testing will stop

## Slide 31: Allowing enough time to test
Allow for all stages in the test process
Don't underestimate the time taken to set up the testing environment, find data etc.
Testing rarely goes 'smoothly'
  plan for faults to occur
  assume 2-3 passes through system test.

## Slide 32: End of Session 2
Any Questions?

## Slide 33: Sources of estimation knowledge
Intuition, guesswork
Previous experience
Company estimating standards

## Slide 34: Test Approaches (strategies)

## Slide 35: Preventative v reactive test approaches
One way to classify test approaches or strategies is based on the point in time at which the bulk of the test design work is begun:
  Preventative approaches, where tests are designed as early as possible.
  Reactive approaches, where test design comes after the software or system has been produced.

## Slide 36: Selecting an approach
The selection of a test approach should consider the context, including:
  The risk of failure of the project, hazards to the product and risks of product failure to humans, the environment and the company
  The skills and experience of the people in the proposed techniques, tools and methods
  The objective of the testing and the mission of the testing team
  Regulatory aspects, such as external and internal regulations for the development process
  The nature of the product and the business.

## Slide 37: Test Progress Monitoring and Control

## Slide 38: Test progress monitoring
The purpose of test monitoring is to give feedback and visibility about test activities
Information to be monitored may be collected manually or automatically and may be used to measure exit criteria, such as coverage
Metrics may also be used to assess progress against the planned schedule and budget

## Slide 39: Common test metrics
Percentage of work done in test case preparation (or percentage of planned test cases prepared)
Percentage of work done in test environment preparation
Test case execution (e.g. number of test cases run/not run, and test cases passed/failed)
Defect information (e.g. defect density, defects found and fixed, failure rate, and retest results)
Test coverage of requirements, risks or code
Testing costs, including the cost compared to the benefit of finding the next defect or to run the next test.

## Slide 40: Test Reporting
Test reporting is concerned with summarizing information about the testing endeavour, including:
  What happened during a period of testing, such as dates when exit criteria were met.
  Analyzed information and metrics to support recommendations and decisions about future actions, such as an assessment of defects remaining, the economic

## Slide 41: IEEE 829 test summary report composition
Summary
Variances
Comprehensive assessment
Summary of results
Evaluation
Summary of Activities
Approvals

## Slide 42: Quantification of the testing
Metrics should be collected during and at the end of a test level in order to assess:
  The adequacy of the test objectives for that test level
  The adequacy of the test approaches taken
  The effectiveness of the testing with respect to its objectives.

## Slide 43: Test control
Test control describes any guiding or corrective actions taken as a result of information and metrics gathered and reported.
Actions may cover any test activity and may affect any other software life cycle activity or task.
Examples of test control actions are
  Re-prioritize tests when an identified risk occurs
  Change the test schedule due to availability of a test environment.
  Set an entry criterion requiring fixes to have been retested by a developer before accepting them into a build.

## Slide 44: End of Session 3
Any Questions?